## Compliance Matrix
ID | Requirement | Category | Status | Priority | What's Wrong | Why It Matters | Request | Owner | Evidence Document | Page | Evidence Quote | Evidence Quality | Notes
Project: | Test Project
Generated: | 12/03/2026
Generated by: | 🤖 AI-Powered Analysis (BSR Quality Checker)
SUMMARY
Total Requirements: | 82
Met: | 23 | 28%
Partial: | 39 | 48%
Not Met: | 20 | 24%
Compliance Rate: | 28%
ID | Requirement | Category | Status | Priority | What's Wrong | Why It Matters | Request | Owner | Evidence Document | Page | Evidence Quote | Evidence Quality | Notes
SM-002 | Means of Escape Clearly Defined | FIRE_SAFETY | Blocker | Critical | No documentation of escape provisions | Missing critical fire safety documentation - mandatory BSR requirement | Address: No documentation of escape provisions | Project Team | Not provided |  |  |  | No fire strategy or means of escape documentation found.
SM-003 | Compartmentation Strategy with Fire Resistance Periods | FIRE_SAFETY | Blocker | Critical | No compartmentation section | Missing critical fire safety documentation - mandatory BSR requirement | Address: No compartmentation section | Project Team | Not provided |  |  |  | No fire strategy or compartmentation documentation found.
SM-004 | External Wall System Fire Performance Specified | FIRE_SAFETY | Blocker | Critical | No cavity barriers | Missing critical fire safety documentation - mandatory BSR requirement | Address: No cavity barriers | Project Team | GOOD-Riverside-Tower.pdf |  | ...rotected shafts: 60 minutes All fire resistance periods determined in accordance with Table A2 of Approved Document B. SECTION 4: EXTERNAL FIRE SPREAD External wall construction: Clay brick oute... |  | External wall documentation incomplete. Missing: cavity barriers, specific materials named.
SM-005 | Sprinkler Provision Addressed Appropriately | FIRE_SAFETY | Blocker | Critical | No mention of sprinkler provision despite building height of 22m exceeding 11m threshold | Missing critical fire safety documentation - mandatory BSR requirement | Add comprehensive sprinkler section to fire strategy addressing provision, coverage, standards, and design intent | FIRE_ENGINEER | Not provided |  |  |  | The fire strategy document does not mention sprinklers at all, despite the building being 22m high (well over the 11m threshold where sprinklers are typically required for residential buildings). T...
SM-006 | Firefighting Access Provisions for HRBs | FIRE_SAFETY | Blocker | Critical | No firefighting access section | Missing critical fire safety documentation - mandatory BSR requirement | Address: No firefighting access section | Project Team | Not provided |  |  |  | No fire strategy or access documentation found.
SM-007 | Second Staircase Provision for Tall Residential | FIRE_SAFETY | Blocker | Critical | No mention of staircase strategy | Missing critical fire safety documentation - mandatory BSR requirement | Address: No mention of staircase strategy | Project Team | Not provided |  |  |  | No fire strategy or core design documentation found.
SM-009 | Structural Fire Resistance Aligned with Fire Strategy | FIRE_SAFETY | Blocker | Critical | No fire resistance mentioned in structural report | Missing critical fire safety documentation - mandatory BSR requirement | Address: No fire resistance mentioned in structural report | Project Team | Not provided |  |  |  | No structural documentation found to assess fire resistance.
SM-019 | Evacuation Strategy Type Explicitly Stated | FIRE_SAFETY | Blocker | Critical | No evacuation strategy stated | Missing critical fire safety documentation - mandatory BSR requirement | Address: No evacuation strategy stated | Project Team | Not provided |  |  |  | No fire strategy or evacuation documentation found.
SM-031 | Fire Door Ratings Specified | FIRE_SAFETY | Blocker | Critical | Fire doors mentioned without FD ratings | Missing critical fire safety documentation - mandatory BSR requirement | Address: Fire doors mentioned without FD ratings | Project Team | GOOD-Riverside-Tower.pdf |  |  |  | Fire doors mentioned but specific ratings (FD30/FD60) not specified.
SM-033 | Fire Stopping and Penetration Seals | FIRE_SAFETY | Blocker | Critical | No fire stopping information | Missing critical fire safety documentation - mandatory BSR requirement | Address: No fire stopping information | Project Team | Not provided |  |  |  | No fire stopping or penetration sealing information found.
SM-012 | Golden Thread Information Strategy Defined | GOLDEN_THREAD | Blocker | Critical | No mention of golden thread or information management | High severity gap - BSR likely to reject or issue significant queries | Address: No mention of golden thread or information management | Project Team | Not provided |  |  |  | No mention of golden thread or information management strategy.
SM-012 | Golden Thread Information Strategy Defined | GOLDEN_THREAD | Blocker | Critical | No mention of golden thread requirements or information management | High severity gap - BSR likely to reject or issue significant queries | Develop and document a comprehensive golden thread information strategy including data structure, storage approach, and handover procedures | PRINCIPAL_DESIGNER | Not provided |  |  |  | The fire safety strategy document contains no mention of golden thread requirements, information management approach, or how building information will be structured, stored, and handed over. While ...
SM-010 | Principal Designer Identified with Competence Evidence | HRB_DUTIES | Blocker | Critical | No Principal Designer named | High severity gap - BSR likely to reject or issue significant queries | Address: No Principal Designer named | Project Team | Not provided |  |  |  | No Principal Designer named in submission pack.
SM-010 | Principal Designer Identified with Competence Evidence | HRB_DUTIES | Blocker | Critical | No Principal Designer identified by name | High severity gap - BSR likely to reject or issue significant queries | Identify and document the appointed Principal Designer with full competence evidence | CLIENT_INFO | Not provided |  |  |  | The fire strategy document does not identify a Principal Designer or provide any evidence of their competence. While the document is prepared for Gateway 2 submission and references compliance with...
SM-011 | Principal Contractor Identified with Competence Evidence | HRB_DUTIES | Blocker | Critical | No Principal Contractor named or referenced | High severity gap - BSR likely to reject or issue significant queries | Address: No Principal Contractor named or referenced | Project Team | Not provided |  |  |  | No Principal Contractor named or referenced in submission pack.
SM-011 | Principal Contractor Identified with Competence Evidence | HRB_DUTIES | Blocker | Critical | No Principal Contractor identified by name or organization | High severity gap - BSR likely to reject or issue significant queries | Identify and document the appointed Principal Contractor with organization details | CLIENT_INFO | Not provided |  |  |  | The fire strategy document does not identify a Principal Contractor or provide any evidence of their competence. While the document is prepared for Gateway 2 submission and references compliance wi...
SM-023 | London Fire Statement Present (London Only) | LONDON_SPECIFIC | Blocker | Critical | No Fire Statement (London project) | High severity gap - BSR likely to reject or issue significant queries | Address: No Fire Statement (London project) | Project Team | Not provided |  |  |  | London project but no Fire Statement (Policy D12) found.
SM-001 | Fire Strategy Report Present and Complete | PACK_COMPLETENESS | Blocker | Critical | No fire strategy report present | High severity gap - BSR likely to reject or issue significant queries | Address: No fire strategy report present | Project Team | Not provided |  |  |  | No fire strategy document found. Searched for "fire strategy", "fire safety strategy", or "fire report" in document names.
SM-008 | Structural Design Information Present | PACK_COMPLETENESS | Blocker | Critical | No structural documentation | High severity gap - BSR likely to reject or issue significant queries | Address: No structural documentation | Project Team | Not provided |  |  |  | No structural report or engineering documentation found.
SM-008 | Structural Design Information Present | PACK_COMPLETENESS | Blocker | Critical | No structural report or statement from chartered structural engineer | High severity gap - BSR likely to reject or issue significant queries | Obtain and include structural report from ABC Structural Engineers Ltd covering foundation approach, superstructure system, and Eurocode compliance | structural engineer | GOOD-Riverside-Tower.pdf |  | Structural calculations provided separately by ABC Structural Engineers Ltd. |  | The fire strategy document mentions structural calculations but does not include the required structural design information. The document states 'Structural calculations provided separately by ABC ...
SM-020 | Building Height Consistent Across Documents | CONSISTENCY | Review Required | High |  | Critical for BSR approval |  |  | Not provided |  |  |  | Assessment failed due to processing error
SM-021 | Storey Count Consistent Across Documents | CONSISTENCY | Review Required | High | No other project documents provided to verify cross-document consistency of storey count | Incomplete critical documentation - may cause rejection or delays | Provide architectural drawings, planning application, and structural reports to verify consistent storey count across all project documents | PROJECT_TEAM | GOOD-Riverside-Tower.pdf |  | Executive Summary: 'Number of Storeys: 7 above ground' and Section 1: 'Storeys: 7 above ground' |  | The document consistently states '7 storeys' and '7 above ground' in multiple sections (Executive Summary and Section 1), which shows internal consistency. However, the criterion requires consisten...
SM-002 | Means of Escape Clearly Defined | FIRE_SAFETY | Review Required | High | No exit widths or staircase capacities specified | Incomplete critical documentation - may cause rejection or delays | Add specific exit widths and staircase capacity calculations in accordance with ADB Table 4 | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | The building is provided with 2 protected staircases serving all residential floors in accordance with Approved Document B requirements for buildings exceeding 18m in height. Maximum travel distanc... |  | The document provides some means of escape information but lacks critical details required by Approved Document B. While it states evacuation strategy (Stay Put), travel distances (18m), and mentio...
SM-003 | Compartmentation Strategy with Fire Resistance Periods | FIRE_SAFETY | Review Required | High | No specific compartment sizes defined | Incomplete critical documentation - may cause rejection or delays | Add specific compartment sizes and maximum areas per compartment | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | Fire resistance periods: - Loadbearing elements: 60 minutes - Compartment walls between apartments: 60 minutes - Compartment floors: 60 minutes - Protected shafts: 60 minutes All fire resistance pe... |  | The document provides explicit fire resistance periods (60 minutes for all elements) and references Table A2 of Approved Document B for justification. However, it lacks specific compartment sizes, ...
SM-004 | External Wall System Fire Performance Specified | FIRE_SAFETY | Review Required | High | No mention of cavity barriers in external wall system | Incomplete critical documentation - may cause rejection or delays | Add cavity barrier specification to external wall section | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | External wall construction: Clay brick outer leaf with stone wool insulation (A1 non-combustible). All materials achieve European Classification A2-s1, d0 (non-combustible) in accordance with Regul... |  | The document provides good external wall material specifications with fire classifications (A1 non-combustible materials including clay brick outer leaf, stone wool insulation, and concrete blockwo...
SM-005 | Sprinkler Provision Addressed Appropriately | FIRE_SAFETY | Review Required | High | No mention of sprinklers in fire strategy | Incomplete critical documentation - may cause rejection or delays | Address: No mention of sprinklers in fire strategy | Project Team | Not provided |  |  |  | No fire strategy or sprinkler documentation found.
SM-006 | Firefighting Access Provisions for HRBs | FIRE_SAFETY | Review Required | High | Firefighting shaft provision not explicitly mentioned despite 22m height exceeding 18m threshold | Incomplete critical documentation - may cause rejection or delays | Complete Section 6 to include firefighting shaft design, fire main locations, and evidence of fire service consultation | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | SECTION 6: FIRE SERVICE ACCESS Vehicle access provided in accordance with Approved Docum |  | The document shows evidence of firefighting access provisions but is incomplete. Section 6 'FIRE SERVICE ACCESS' is present and begins with 'Vehicle access provided in accordance with Approved Docu...
SM-009 | Structural Fire Resistance Aligned with Fire Strategy | FIRE_SAFETY | Review Required | High | Structural report not provided in document pack to verify alignment | Incomplete critical documentation - may cause rejection or delays | Obtain structural report from ABC Structural Engineers Ltd to verify 60-minute fire resistance achievement | project team | GOOD-Riverside-Tower.pdf |  | All structural elements designed for 60 minutes fire resistance in accordance with: - BS EN 1992-1-2: Eurocode 2 - Structural fire design for concrete - BS EN 1993-1-2: Eurocode 3 - Structural fire... |  | The fire strategy document explicitly states fire resistance requirements for structural elements (60 minutes) and references that structural calculations are provided separately by ABC Structural ...
SM-017 | Fire Detection and Alarm System Specified | FIRE_SAFETY | Review Required | High | No fire alarm information | Moderate gap - may trigger BSR queries or request for additional information | Address: No fire alarm information | Project Team | Not provided |  |  |  | No fire strategy or alarm specification found.
SM-017 | Fire Detection and Alarm System Specified | FIRE_SAFETY | Review Required | High | No fire alarm system category specified (L1/L2/L3 per BS 5839) | Moderate gap - may trigger BSR queries or request for additional information | Specify fire detection and alarm system including BS 5839 category, detector types, coverage, and integration with stay-put evacuation strategy | FIRE_ENGINEER | Not provided |  |  |  | The fire strategy document contains no information about fire detection and alarm systems. While it covers means of escape, compartmentation, external fire spread, and structural fire resistance, t...
SM-018 | Smoke Control Strategy Defined | FIRE_SAFETY | Review Required | High | No smoke control mentioned | Moderate gap - may trigger BSR queries or request for additional information | Address: No smoke control mentioned | Project Team | Not provided |  |  |  | No fire strategy or smoke control documentation found.
SM-018 | Smoke Control Strategy Defined | FIRE_SAFETY | Review Required | High | No smoke control strategy defined for common corridors | Moderate gap - may trigger BSR queries or request for additional information | Develop comprehensive smoke control strategy for common areas and escape routes | fire engineer | Not provided |  |  |  | The fire strategy document does not contain any explicit mention of smoke control systems or strategies for common areas and escape routes. While the document covers means of escape, compartmentati...
SM-019 | Evacuation Strategy Type Explicitly Stated | FIRE_SAFETY | Review Required | High | No justification provided for why stay-put evacuation strategy is appropriate for this building design | Incomplete critical documentation - may cause rejection or delays | Add justification for stay-put evacuation strategy based on building design features (compartmentation, protected staircases, fire resistance) | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | Evacuation Strategy: Stay Put |  | The document explicitly states 'Evacuation Strategy: Stay Put' in Section 2, which satisfies the requirement to state the evacuation strategy type. However, the criterion requires three elements: (...
SM-013 | Change Control Process Defined | HRB_DUTIES | Review Required | High | No description of change control process for construction phase | Moderate gap - may trigger BSR queries or request for additional information | Develop formal change control procedure document addressing BSR notification requirements and change assessment responsibilities | PRINCIPAL_DESIGNER | Not provided |  |  |  | The fire strategy document contains no mention of change control processes, BSR notification requirements for major changes, or responsibility for change assessment during construction. The documen...
SM-028 | Construction Phase Plan Approach Outlined | HRB_DUTIES | Review Required | High | No construction management information | Moderate gap - may trigger BSR queries or request for additional information | Address: No construction management information | Project Team | Not provided |  |  |  | No construction phase management information found.
SM-028 | Construction Phase Plan Approach Outlined | HRB_DUTIES | Review Required | High | No construction phase management approach outlined | Moderate gap - may trigger BSR queries or request for additional information | Develop construction phase management section outlining supervision approach, quality assurance procedures, and design intent maintenance | PRINCIPAL_CONTRACTOR | Not provided |  |  |  | The fire strategy document contains no information about construction phase management, site supervision, quality assurance, or how the design intent will be maintained during construction. The doc...
SM-024 | PEEP Considerations Addressed (London Residential) | LONDON_SPECIFIC | Review Required | High | No mention of PEEPs or disabled evacuation | Moderate gap - may trigger BSR queries or request for additional information | Address: No mention of PEEPs or disabled evacuation | Project Team | Not provided |  |  |  | No fire documentation found to assess PEEP provisions.
SM-001 | Fire Strategy Report Present and Complete | PACK_COMPLETENESS | Review Required | High | Section 6 (Fire Service Access) is incomplete - text cuts off mid-sentence | Incomplete critical documentation - may cause rejection or delays | Complete Section 6 Fire Service Access with full requirements | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | FIRE SAFETY STRATEGY REPORT Project: Riverside Tower - Gateway 2 Submission... SECTION 2: MEANS OF ESCAPE... SECTION 3: COMPARTMENTATION... SECTION 4: EXTERNAL FIRE SPREAD... SECTION 5: STRUCTURAL ... |  | The fire strategy report is present and addresses most required sections (means of escape, compartmentation, external fire spread, structural fire resistance, and firefighter access), but has sever...
SM-014 | Design and Access Statement Present | PACK_COMPLETENESS | Review Required | High | No DAS present | Moderate gap - may trigger BSR queries or request for additional information | Address: No DAS present | Project Team | Not provided |  |  |  | No Design and Access Statement found in submission pack.
SM-014 | Design and Access Statement Present | PACK_COMPLETENESS | Review Required | High | No Design and Access Statement document present in the pack | Moderate gap - may trigger BSR queries or request for additional information | Prepare comprehensive Design and Access Statement covering building description, context, design rationale, and access provisions | ARCHITECT | Not provided |  |  |  | The provided document is a Fire Safety Strategy Report, not a Design and Access Statement (DAS). While the fire strategy contains building description and design rationale for fire safety aspects, ...
SM-015 | MEP Systems Specification Present | PACK_COMPLETENESS | Review Required | High | No MEP documentation | Moderate gap - may trigger BSR queries or request for additional information | Address: No MEP documentation | Project Team | Not provided |  |  |  | No MEP documentation found in submission pack.
SM-015 | MEP Systems Specification Present | PACK_COMPLETENESS | Review Required | High | No MEP specification or report present in the pack | Moderate gap - may trigger BSR queries or request for additional information | Prepare comprehensive MEP specification covering heating, ventilation, electrical, and plumbing systems with coordination details | MEP_CONSULTANT | Not provided |  |  |  | The provided document is a fire strategy report that does not contain MEP (Mechanical, Electrical, and Plumbing) systems specification. While the fire strategy mentions some MEP-related elements li...
SM-022 | Fire Risk Assessment Included | PACK_COMPLETENESS | Review Required | High | No FRA present | Moderate gap - may trigger BSR queries or request for additional information | Address: No FRA present | Project Team | Not provided |  |  |  | No Fire Risk Assessment found in submission pack.
SM-022 | Fire Risk Assessment Included | PACK_COMPLETENESS | Review Required | High | No Fire Risk Assessment document present in the pack | Moderate gap - may trigger BSR queries or request for additional information | Commission a building-specific Fire Risk Assessment that identifies fire hazards, assesses likelihood and consequence of fire scenarios, and demonstrates how the fire strategy measures address identified risks | fire_engineer | Not provided |  |  |  | The fire strategy document does not include a Fire Risk Assessment (FRA). While the document provides a comprehensive fire safety strategy with technical details about means of escape, compartmenta...
SM-026 | Regulatory Compliance Mapping Present | TRACEABILITY | Review Required | High | No compliance mapping | Moderate gap - may trigger BSR queries or request for additional information | Address: No compliance mapping | Project Team | Not provided |  |  |  | No compliance mapping or Building Regulations matrix found.
SM-016 | Ventilation Strategy Defined per ADF | VENTILATION | Review Required | High | No ventilation information | Moderate gap - may trigger BSR queries or request for additional information | Address: No ventilation information | Project Team | Not provided |  |  |  | No ventilation information found in submission pack.
SM-020 | Building Height Consistent Across Documents | CONSISTENCY | Met | High |  | Critical for BSR approval |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Height found in GOOD-Riverside-Tower.pdf only. Cannot verify cross-document consistency.
SM-021 | Storey Count Consistent Across Documents | CONSISTENCY | Met | High |  | Critical for BSR approval |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Storey count found in GOOD-Riverside-Tower.pdf only. Cannot verify cross-document consistency.
SM-007 | Second Staircase Provision for Tall Residential | FIRE_SAFETY | Met | High |  | Critical for BSR approval |  |  | GOOD-Riverside-Tower.pdf |  | The building is provided with 2 protected staircases serving all residential floors in accordance with Approved Document B requirements for buildings exceeding 18m in height. |  | The fire strategy explicitly addresses the second staircase requirement for this 22m high residential building. The document clearly states 'The building is provided with 2 protected staircases ser...
SM-036 | Dry or Wet Riser Provision | FIRE_SAFETY | Met | High |  | Critical for BSR approval |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Dry riser provision specified.
SM-038 | Basement Fire Safety Strategy | FIRE_SAFETY | Met | High |  | Critical for BSR approval |  |  | Not provided |  |  |  | No basement identified. Check not applicable.
SM-027 | Document Version Control Evident | GOLDEN_THREAD | Review Required | Medium | No revision number or version number present | Minor issue - unlikely to block submission but may be noted | Add comprehensive version control header with revision number, version history table, and change tracking | PROJECT_TEAM | GOOD-Riverside-Tower.pdf |  | Date: October 2025 Status: For Gateway 2 Submission |  | The document lacks essential version control elements required for golden thread compliance. While it has a date (October 2025) and status (For Gateway 2 Submission), it completely lacks revision n...
SM-025 | Documents Cross-Reference Each Other | TRACEABILITY | Review Required | Medium | No specific document references with drawing numbers or report references | Minor issue - unlikely to block submission but may be noted | Add specific cross-references to structural engineering reports with document numbers and revision dates | FIRE_ENGINEER | GOOD-Riverside-Tower.pdf |  | Structural calculations provided separately by ABC Structural Engineers Ltd. |  | The fire strategy document operates as a standalone document with no cross-references to other technical documents. While it mentions 'Structural calculations provided separately by ABC Structural ...
SM-053 | Project Name Consistently Used | CONSISTENCY | Review Required | Low | No clear project name | Minor issue - unlikely to block submission but may be noted | Address: No clear project name | Project Team | Not provided |  |  |  | Project name not clearly identified across documents.
SM-034 | Resident Communication of Evacuation Strategy | FIRE_SAFETY | Review Required | Low | Strategy exists but communication plan unclear | Partial compliance - BSR may request clarification | Address: Strategy exists but communication plan unclear | Project Team | GOOD-Riverside-Tower.pdf |  |  |  | Evacuation strategy stated but resident communication approach not addressed.
SM-045 | As-Built Documentation Commitment | GOLDEN_THREAD | Review Required | Low | No as-built documentation commitment | Partial compliance - BSR may request clarification | Address: No as-built documentation commitment | Project Team | Not provided |  |  |  | No as-built documentation commitment found.
SM-046 | BIM Strategy for Golden Thread | GOLDEN_THREAD | Review Required | Low | No BIM strategy | Minor issue - unlikely to block submission but may be noted | Address: No BIM strategy | Project Team | Not provided |  |  |  | No BIM strategy identified.
SM-047 | Drawing Revision Control System | GOLDEN_THREAD | Review Required | Low | No revision control system | Minor issue - unlikely to block submission but may be noted | Address: No revision control system | Project Team | Not provided |  |  |  | No drawing revision control system evident.
SM-013 | Change Control Process Defined | HRB_DUTIES | Review Required | Low | No acknowledgment of major change notification requirement | Partial compliance - BSR may request clarification | Address: No acknowledgment of major change notification requirement | Project Team | GOOD-Riverside-Tower.pdf |  |  |  | Change control mentioned but incomplete. Found: responsibilities assigned.
SM-041 | Competent Person Scheme References | HRB_DUTIES | Review Required | Low | No competent person scheme references | Partial compliance - BSR may request clarification | Address: No competent person scheme references | Project Team | Not provided |  |  |  | No reference to competent person schemes or third party certification.
SM-030 | Site Location and Context Documented | PACK_COMPLETENESS | Review Required | Low | No site plan provided | Minor issue - unlikely to block submission but may be noted | Prepare comprehensive site plan showing building location, boundaries, access routes, and adjacent structures | ARCHITECT | GOOD-Riverside-Tower.pdf |  | Project: Riverside Tower, London, UK... SECTION 6: FIRE SERVICE ACCESS Vehicle access provided in accordance with Approved Docum |  | The fire strategy document provides some site context information but lacks comprehensive site location documentation. While it identifies the project location as 'London, UK' and references fire s...
SM-026 | Regulatory Compliance Mapping Present | TRACEABILITY | Review Required | Low | No comprehensive compliance matrix mapping all Building Regulations Schedule 1 requirements | Partial compliance - BSR may request clarification | Create comprehensive Building Regulations compliance matrix mapping all Schedule 1 requirements to specific design documents and sections | PRINCIPAL_DESIGNER | GOOD-Riverside-Tower.pdf |  | This fire safety strategy demonstrates compliance with the functional requirements of Building Regulations for a 22m high residential building comprising 7 storeys and 48 apartments. Prepared in ac... |  | The fire strategy document demonstrates compliance with fire safety regulations (Building Regulations Part B) but lacks a comprehensive compliance mapping to all Building Regulations Schedule 1 req...
SM-048 | Overheating Risk Assessment | VENTILATION | Review Required | Low | No overheating assessment | Partial compliance - BSR may request clarification | Address: No overheating assessment | Project Team | Not provided |  |  |  | No overheating assessment found. Required for residential buildings.
SM-050 | Kitchen Extract and Makeup Air | VENTILATION | Review Required | Low | No kitchen extract strategy | Minor issue - unlikely to block submission but may be noted | Address: No kitchen extract strategy | Project Team | Not provided |  |  |  | No kitchen extract strategy identified.
SM-051 | Building Use Consistently Described | CONSISTENCY | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Building use consistently described as residential.
SM-052 | Site Address Consistently Referenced | CONSISTENCY | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Address referenced but postcode not consistently extracted.
SM-032 | Emergency Lighting Specification | FIRE_SAFETY | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Emergency lighting specified with duration or BS 5266 reference.
SM-035 | Wayfinding and Escape Signage | FIRE_SAFETY | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Signage mentioned but standards compliance not confirmed.
SM-037 | Balcony and Terrace Fire Safety | FIRE_SAFETY | Met | Low |  |  |  |  | Not provided |  |  |  | No balconies or terraces identified. Check not applicable.
SM-039 | Car Park Fire Safety (if applicable) | FIRE_SAFETY | Met | Low |  |  |  |  | Not provided |  |  |  | No car park identified. Check not applicable.
SM-040 | Refuse Store Fire Safety | FIRE_SAFETY | Met | Low |  |  |  |  | Not provided |  |  |  | No refuse store identified. Check not applicable.
SM-027 | Document Version Control Evident | GOLDEN_THREAD | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Documents are dated but formal revision tracking may be limited.
SM-042 | Building Safety Manager Considerations | HRB_DUTIES | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Building Safety Manager or Accountable Person provisions addressed.
SM-043 | Partial Occupation Strategy (if applicable) | HRB_DUTIES | Met | Low |  |  |  |  | Not provided |  |  |  | No partial occupation indicated. Check may not be applicable.
SM-044 | Specialist Subcontractor Competence Approach | HRB_DUTIES | Met | Low |  |  |  |  | Not provided |  |  |  | No specific subcontractor provisions identified.
SM-029 | Building Description Clear and Complete | PACK_COMPLETENESS | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Building clearly described with: use/purpose, height/storeys, units/area, construction type.
SM-029 | Building Description Clear and Complete | PACK_COMPLETENESS | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  | This fire safety strategy demonstrates compliance with the functional requirements of Building Regulations for a 22m high residential building comprising 7 storeys and 48 apartments. Building Class... |  | The fire strategy document provides a clear and complete building description that satisfies all requirements. The building description is consistently presented in multiple sections with key param...
SM-030 | Site Location and Context Documented | PACK_COMPLETENESS | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Some site context present. Found: access routes.
SM-025 | Documents Cross-Reference Each Other | TRACEABILITY | Met | Low |  |  |  |  | Not provided |  |  |  | Only one document in pack. Cross-referencing not applicable.
SM-054 | Design Team Identified | TRACEABILITY | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Design team members identified.
SM-055 | Documents Dated Within Last 12 Months | TRACEABILITY | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | 1 documents dated 2025-2026.
SM-049 | Common Area Ventilation | VENTILATION | Met | Low |  |  |  |  | GOOD-Riverside-Tower.pdf |  |  |  | Common area ventilation strategy specified.